WEBSITE

# Design & Development

Proposal & Quotation

Prepared for  BHMR Studios Private Limited

Prepared by  Vikas Maloo

Date  30 August 2026

Project objective

Build the new BHMR Studios website from a clean foundation: a consistent design system in Figma, responsive engineering, tasteful motion, working enquiry/career forms, light integrations, QA, and deployment to the BHMR domain or an agreed subdomain.

PROPOSED PROFESSIONAL FEE

₹45,000

Commercial Note

I’ve kept the professional fee at ₹45,000 for this initial engagement, keeping in mind the overall scope, effort involved, and that this is our first project together. I’d like to keep it practical and fair from both sides, while making sure we have a good foundation for working together beyond this project as well. The quotation is tentative and open for discussion, so we can always adjust, add, remove, or reprioritise items based on what makes the most sense as we move forward. My main intention is to make this work well for both of us and build a relationship that can continue beyond just this website.

# 1. Understanding of the Project

The current UI and animation direction has a strong base, but the new website will be rebuilt cleanly rather than extending the previous implementation. The aim is to retain useful visual ideas while fixing consistency, responsiveness, maintainability, form behaviour, and delivery visibility.

• The supplied Made With GSAP website will be used as a visual and interaction reference, not as a page-by-page copy.

• The new Figma will be component-led and built around a reusable design system.

• The website will be developed with a responsive layout for desktop, tablet and mobile.

• For now, website form responses can be captured in Google Sheets. If the BHMR HubSpot account is already ready, I can connect the same flow to HubSpot from the beginning.

• No separate custom database is proposed for the current requirement. We can revisit this later if a future scope needs one.

# 2. Pages in Current Scope

| Page | Planned treatment |
| --- | --- |
| Homepage | Hero, positioning, process, capabilities, audiences, CTA and lead capture |
| About | Positioning, principles, standards, founder, commitments and fit |
| Services | Service groups, guidance, FAQs, CTA and lead capture |
| Pricing | Packages, comparison/content presentation, FAQs and CTA |
| Work With Us | Qualification flow, multi-step form, discovery information and FAQs |
| Careers | Culture, hiring process, open roles and FAQs |
| Director of Business Development | Role details, requirements, compensation and application CTA |
| Privacy Policy | Policy content, data/contact information |
| Terms of Service | Website terms, payments, IP, confidentiality and disputes |

# 3. Phase-wise Scope & Fees

The effort ranges below are practical planning estimates for the agreed scope. I have kept the estimate based on the actual work involved, while using reusable components and modern development tools to keep repeatable implementation efficient.

Effort note: The hours are indicative for planning and transparency, not an hourly billing model. The agreed professional fee remains fixed at ₹45,000 for the current scope.

| Phase & Deliverables | Estimated Effort | Fee |
| --- | --- | --- |
| 1. Discovery & UX Direction Requirement consolidation, sitemap/information architecture, page-by-page functional mapping, CTA/form mapping, content review, assumptions, technical direction and milestone planning. | 12-16 hrs | ₹9,000 |
| 2. Figma + Design System Complete visual direction, reusable components, typography, colour/spacing system, buttons, forms, navigation, cards, responsive layouts for key templates, and engineering-ready Figma structure. | 20-24 hrs | ₹8,000 |
| 3. Prototype + Interaction Direction Clickable prototype for core journeys, navigation states, form flow, section transitions, interaction behaviour, motion notes and mobile interaction considerations. | 10-12 hrs | ₹4,000 |
| 4. Engineering Component-based frontend build, page implementation, responsive layouts, shared header/footer, content integration, navigation, UI states, accessibility basics, animation implementation and performance-minded asset handling. | 30-36 hrs | ₹17,000 |
| 5. Forms + Integrations + QA Form validation and submission handling, Google Sheets connection (₹1,000), HubSpot connection if account is ready (₹5,000), success/error states, spam/rate-limit basics, responsive QA, browser checks and final fixes. | 16-20 hrs | ₹6,000 |
| 6. Deployment + Handover Production setup, DNS management, deployment to bhmrstudios.com or an agreed subdomain, environment/configuration checks, source/Figma handover and final walkthrough. | 8 hrs | ₹1,000 |
| TOTAL PROFESSIONAL FEE | 96-116 hrs (approx.) | ₹45,000 |

# 4. Form & Integration Setup

For the current scope, the simplest approach is to avoid introducing a separate database unless the project actually needs one.

| Item | Included approach |
| --- | --- |
| Google Sheets - ₹1,000 | Form responses can be mapped into an agreed Google Sheet with timestamps and the relevant enquiry/application fields. |
| HubSpot - ₹5,000 | If BHMR has an active HubSpot account and can provide an invite/access, the website enquiry flow can be connected directly to HubSpot from the beginning. Field mapping will follow the agreed contact/property structure. |
| Website Forms - included within Phase 5 | Shared form handling, field validation, required/optional states, success and error messages, submission handling and basic spam/rate-limit protection for the agreed forms. |
| Careers Applications - within current scope | Application submission flow is included. Any resume/file upload handling will use the simplest suitable external storage or platform-supported mechanism agreed during implementation; a custom applicant database is not assumed. |

No separate database is proposed for the current website. We can revisit this later if the site grows into a larger CMS, candidate management system, dashboard, custom admin workflow, or another use case that genuinely benefits from persistent application data.

# 5. Deployment, DNS & Handover

• DNS management and the required domain/subdomain configuration will be handled as part of deployment.

• The website will be deployed to the BHMR production domain (bhmrstudios.com) or an agreed BHMR subdomain.

• Final hosting/platform choice will follow the technical direction agreed during discovery and any existing BHMR infrastructure constraints.

• Production environment/configuration, build setup and final smoke checks are included.

• Source code and the final Figma file will be handed over at completion.

# 6. Indicative Timeline

| Phase | Indicative duration | Output |
| --- | --- | --- |
| Discovery & UX | 2-3 working days | Confirmed structure, flows, scope and plan |
| Figma + Design System | 5-7 working days | Approved visual system and page designs |
| Prototype | 2-3 working days | Clickable core flows and interaction direction |
| Engineering | 7-10 working days | Responsive working website |
| Forms + Integrations + QA | 3-5 working days | Working forms, integrations and tested build |
| Deployment + Handover | 1-2 working days | Live website and handover |

Estimated overall delivery: approximately 5-7 weeks, depending mainly on feedback turnaround, access to services and the final number of approved interaction refinements.

# 7. Payment Schedule

To keep the initial commitment light, only ₹5,000 is taken at the start. After that, the remaining work is billed phase-by-phase based on the agreed deliverables.

| Payment point | Amount | Linked work |
| --- | --- | --- |
| Project confirmation / kickoff | ₹5,000 | Project confirmation, initial planning, access setup and reservation of the project slot |
| Phase 1 balance | ₹4,000 | Discovery & UX direction |
| Phase 2 | ₹8,000 | Figma + Design System |
| Phase 3 | ₹4,000 | Prototype + Interaction Direction |
| Phase 4 | ₹17,000 | Engineering |
| Phase 5 | ₹6,000 | Forms + Integrations + QA |
| Phase 6 / Deployment | ₹1,000 | Deployment + Handover |

Payment note: Each phase is started after its corresponding milestone amount is confirmed, so the work stays aligned with visible deliverables rather than requiring a large upfront payment.

# 8. Reviews, Revisions & Scope Changes

• Up to 2 consolidated review rounds are included within the Figma/prototype stage for the agreed direction.

• Engineering fixes for issues against the approved design and agreed scope are covered during QA.

• Small copy/layout corrections that do not materially change the approved design can be handled within the project.

• New pages, new user journeys, new integrations, new backend/data requirements, or a materially different design direction can be added after a quick discussion and agreed separately.

• The same applies where previously approved work needs to be substantially reworked multiple times because the direction changes after approval. The intention is simply to keep the original estimate fair and transparent for both sides.

# 9. Exclusions

| Included in current fee | Not included unless separately agreed |
| --- | --- |
| • 9-page website redesign and build | • Paid HubSpot plans or premium CRM features |
| • Responsive implementation | • Hosting/domain/SaaS/plugin subscription fees |
| • Figma + reusable design system | • Professional photography, video production or original illustration |
| • Clickable prototype | • Copywriting or substantial rewriting beyond supplied copy |
| • Forms and agreed form flows | • Large custom CMS/admin/dashboard |
| • Google Sheets integration (₹1,000) | • Custom applicant-management system or separate database beyond agreed needs |
| • HubSpot integration if account/access is ready (₹5,000) | • Custom scheduling/calendar platform |
| • QA, basic accessibility checks and device/browser hardening | • Advanced analytics, marketing automation or additional third-party systems |
| • DNS configuration and deployment to BHMR domain/subdomain | • New pages/features/integrations added after scope approval |
| • Source code + Figma handover | • Ongoing feature development beyond the included support period |

# 10. Post-Launch Support

post-launch support is included for minor issues directly related to the delivered scope.

• Bug fixes against the approved implementation

• Minor responsive corrections

• Form/integration troubleshooting within the agreed integration scope

• Small content/layout corrections that do not materially change the approved design

New features, new pages, new integrations or substantial redesign work after launch are outside this support window and can be handled separately.

# 11. Client Inputs Needed

• Final page copy and reference assets from the shared Google Drive

• Timely Figma/prototype approvals and consolidated feedback

• Google Sheet access or a confirmed sheet/template for form responses

• HubSpot account invite/access if HubSpot is to be connected from the beginning

• Hosting/domain/DNS access required for final deployment

• Any existing email, analytics, scheduling or third-party credentials that are specifically required by the approved scope

# 12. Quality & Delivery Standards

• Consistent reusable UI components rather than page-by-page styling

• Desktop, tablet and mobile responsive implementation

• Modern browser compatibility checks

• Basic accessibility and keyboard/focus considerations

• Form success/error states and validation

• Performance-conscious images/assets and motion

• Final source, Figma and deployment handover

# 13. Next Steps

• Confirm acceptance of the proposal and current ₹45,000 scope.

• Share the project tracker once onboarding begins so the working plan can be mapped to it.

• Provide Google Sheets details and/or HubSpot access when ready.

• Share any hosting/DNS access needed for deployment.

• Start with the ₹5,000 project confirmation and move into Phase 1.

Thank you for the opportunity. I am looking forward to building this properly and keeping the process clear from day one.

Prepared by Vikas Maloo
Website Design & Development